## Project Outline
Montessori education is a pedagogical approach characterized by students teaching themselves through hands-on, self-led activities. Students are encouraged to embrace their creativity by experimenting with specially designed tools to learn new information through the process of discovery. One such tool involves a set of blocks representing the alphabet and a dictionary—students can arrange the blocks to form words and reference the dictionary to find out more about these words. This project aims to facilitate Montessori education by augmenting the word-forming learning tool, turning the letter blocks into a tangible user interface and replacing the dictionary with a responsive application that can offer multimodal information about newly created words such as pronunciations and images. It is critical to note that this project, SpellCraft, intends to enhance the current tool and promote Montessori principles rather than replacing it with an entirely screen-based approach. Spellcraft will be realized through the combination of relevant hardware and software technologies, such as the Unity game engine and RFID detection.
The main functionality of the project is to display the word and image created by the user’s letter block combination. If possible, a sound should be displayed with the image, such as a barking sound with a dog. If a non-existent word is constructed, the program should only display the word. To achieve the project goals, the software must first be able to detect the order in which the letter blocks are positioned; the letter blocks have RFID tags that are placed on a surface that has an RFID reader, which feeds into the program. The program will read the input and form a string that will be used to display images and sounds from relevant APIs.

## Plan
Member | Course Milestones | Tasks | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14
 | time axis 2024-01-08 to 2024-04-24
|  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday
Tony | Define Project | First meeting, begin plan | bar: 2024-01-17
Ian |  | Defining the Goal (Software Requirements) | bar: 2024-01-18 to 2024-01-19; 2024-01-22
Michael |  | Defining Motivation/Justification | bar: 2024-01-22
All |  | Doing Research (Literature Review) | bar: 2024-01-22 to 2024-01-24
Completing the proposal | bar: 2024-01-25 to 2024-01-26
Project Plan (Timeline) | bar: 2024-01-29 to 2024-01-30
| Design Project | Setting up Unity (Understand environment) | bar: 2024-01-29 to 2024-02-02
Unity UI/Event/Scripting Learning | bar: 2024-02-01 to 2024-02-02
API Research (which ones to use) | bar: 2024-02-01 to 2024-02-02
Simple Unity UI/Event/Scripting practice | bar: 2024-02-05 to 2024-02-07
Unity API Scripting Research/Learning/Practice | bar: 2024-02-05 to 2024-02-07
Hardware Research (Arduino, CPU for Unity app, Table design, Screen, RFID/Blocks, Interface w/ Unity) | bar: 2024-02-01 to 2024-02-02; 2024-02-05 to 2024-02-07
Making architecture diagram | bar: 2024-02-07 to 2024-02-09
Make User Interface designs | bar: 2024-02-07 to 2024-02-09
Begin implementing Unity UI (keyboard input) | bar: 2024-02-12 to 2024-02-16
Begin Implementing Unity API Connection | bar: 2024-02-12 to 2024-02-16
Solidify needs, Request hardware (Bill of Materials) | bar: 2024-02-12 to 2024-02-13
Flex/Support | bar: 2024-02-14 to 2024-02-16
Make Presentation 1 | bar: 2024-02-15 to 2024-02-16
| Continue Work | Finish implementing UI | bar: 2024-02-19 to 2024-02-23; 2024-02-26 to 2024-03-01
Begin implementing Tangible Input Support (Unity code to receive/interpret Arduino signals as input) | bar: 2024-02-19 to 2024-02-23
Integrate API with UI—Software complete | bar: 2024-02-19 to 2024-02-23; 2024-02-26 to 2024-03-01
Begin Hardware Assembly (RFID and Arduino) | bar: 2024-02-26 to 2024-03-01
Connect Assembled hardware to Unity App | bar: 2024-03-04 to 2024-03-05
Assemble Device (put everything in the desk) | bar: 2024-03-06 to 2024-03-08
|  | Spring Break | 2024-03-11: SPRING BREAK
Make Test Plan | bar: 2024-03-18 to 2024-03-19
Start trying to get subjects | bar: 2024-03-20 to 2024-03-22
Make Presentation 2 | bar: 2024-03-20 to 2024-03-22
| Testing | Flesh out experimental procedure | bar: 2024-03-25 to 2024-03-29
Continue contacting subjects | bar: 2024-03-25 to 2024-03-29
Testing/Data Collection | bar: 2024-04-01 to 2024-04-05
Data Analysis | bar: 2024-04-08 to 2024-04-12
| Final writeup | Project Documentation/Submit to Dr. Alex | bar: 2024-04-15 to 2024-04-19
Create Final Presentation Video | bar: 2024-04-22 to 2024-04-23
Showcase | bar: 2024-04-24